## Sheet1
SN	Issues	Status
1	There is a practice of 1 or 2 hour relaxation on employee check-in/check-out time during Nepal bandh	Completed, need testing on JGI
2	Leave earned by working on holidays can be compensated with substitute leave for employees level 8 and above. All employees below 8 will be compensated by OT	Completed, need testing on JGI
3	User Manual	Completed
4	Attendance report	Completed, waiting for JGI feedback
5	Day off in attendance report is showing "absent"	Completed
6	For few employee's OT is defaulted to certain hours to be taken care in HRIS	Completed need testing on JGI
7	Branch should include Head Office, Factory, Valley 1,Valley 2, Valley 3, Zone 1 to Zone 7	Completed, awaiting JGI response
8	Department- two options are shown in dropdown of Department i.e. HR, Finance account	Completed, need confirmation from JGI
9	Nepali Date on Employee Setup	Completed
10	Excel Export issue	Completed, need testingfrom JGI
11	Password Changing Option	Completed, awaiting JGI assurance
12	Define Level/Position wise work on holiday action like substitute leave or Overtime	Completed , need JGI verification
13	For compulsory OT employees, wizard must be created	Completed, needs JGI assurance